## Sheet1
ClipMdPlus
Project Control
Phase 1 beta |  |  |  | Assign: David G Horsman. | It looks like about 2 months work for a nube.
Task | Task | Started | Completed | Notes and lists of Objects | Comments | Crates
1 | Create core clip objects. | 2023-07-01 | 2023-07-15 | ClipMeta, Formats, DataObjects, Hyperlink. The objects DateStd, Range, Sequence will likely be removed at a later date. | Work on this project is related to important goals in related projects. ETL, code conversion, C# conversion to idiomatic RUST, advanced UI design, performance and other issues. | # System sled = "0.34.6" sys = "0.0.0" # async tokio = { version = "1.28.2", features = ["full"] } chrono = {version = "0.4.23", features = ["serde"]}
2 | Add serialization and json, remove. | 2023-07-10 | 2023-08-05 | Precusors to traits, examine DataObjects. There is a central concern of handling the various types of data that can be place on it by the OS. In particular objects of an unknown type need to be properly serialized. | There is a lot of commented out code much of it related to learning the crates. | reqwest = {version = "0.11.18", features = ["json"]} # Serialization serde = {version = "1.0.160", features = ["derive"]} serde_json = "1.0.96"
3 | Select Ui's add native hello world. | 2023-07-24 | 2023-08-02 | ClipForm, Egui, Web, Native, Native(ClipForm, FormWindow, WindowOptions, Main). The structure and a "hello world" text was display. Clean build. |  | egui = { version = "0.22.0"} # , features = ["provide_any"] eframe = "0.22.0" # egui_web = "0.17.0"
4 | Add standard traits and funcitons. | 2023-07-25 |  | Types, TypeForm, DbApi (Crud,Type, Error, Json) | # [Unused] # ansi_escapes = "0" # ansi_escape = "0" # local-ip-address = "0.5.1" # whoami = "1.4.0" # extra = "0.1.0" | thiserror = "1.0.40" derive_more = "0.99.17" .
5 | Add manual implemented Postgres for ClipMeta info. | 2023-08-01 |  | Create scripts, database install. Review existing objects for SQL idiomatic use. Specifically handling of Blobs. | Ultimately an in memory database might be good. I'm interested in having the app fall back to using a Json text persistence. | postgres = "0.19.4" blob = "0.3.0"
6 | Add connection to clipboard (Windows OS). Abstract this. | 2023-07-05 |  | There is an extremley detailed crate (library) that mirrors access to the OS. It's a better choice than hand coding the interface. The Windows native UI was rejeccted as the RUST UI. However it might be needed for handling clipboard event contextual menus. | Uses a registered listener. Access to system info and formats is a concern. There is the broader issue of handling connections to multiple OS platforms. Windows, Linux and Android. iOS? | libc = "0.2.141" [dependencies.windows] version = "0.48" features = [ "Data_Xml_Dom", "Win32_Foundation", "Win32_Security", "Win32_System_Threading", "Win32_UI_WindowsAndMessaging",] [dependencies.windows-sys] version = "0.48" features = [ "Win32_Foundation", "Win32_Security", "Win32_System_Threading", "Win32_UI_WindowsAndMessaging", ]
7 | Creat proc macro crate - clipmdplus_macro | 2023-08-01 |  | Name; VariantName; ToString; Deserialize_enum; Serialize_enum; | This will provide converion macros that the clipboard and other crates will make use of.
| Evaluate Rust clipboard crates | 2023-08-05 |  | Looking at both cross-platform and OS specific options. What is already being used?
Add Web UI
Add Web API